## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File
3636970 | 68240 | ATM Project | 1 | ATM_1-1 | 292268 | Bug |  |  |  |  | Depositing to savings | When trying to deposit 27.88 into savings, total balance calculated is incorrect. Initial state: system is serving a customer who has an account. Bug was found by turning on ATM, entering card number (1), entering correct PIN(42), pressing 2 for deposit, pressing 2 for savings, and entering 27.88 to deposit money. The expected outcome is 1027.88 total balance, but the result is 1017.88. | 3 | Resolved | 3 | Normal |  |  |  |  | 319573 | Jacob Lansang | 319573 | Jacob Lansang | Jan. 20, 2022 12:32 |  | 319573 | Jacob Lansang | Jan. 26, 2022 15:24 | 0 | 0
3636986 | 68240 | ATM Project | 2 | ATM_1-2 | 292268 | Bug |  |  | 63673 | 1.0 | Deposit to savings | Program crashes and does not accept any inputs while trying to deposit too much money into savings. The system started from login with a valid customer card and ID (card number 1 and PIN 42). The bug was found by pressing 2 to deposit money, pressing 2 to go to savings, and trying to deposit $999999999999999999.99. We expect the program to not crash. But it crashed. Program still crashes in version 1.1. | 2 | In Progress | 3 | Normal |  |  |  |  | 319573 | Jacob Lansang | 319573 | Jacob Lansang | Jan. 20, 2022 12:49 |  | 319573 | Jacob Lansang | Jan. 26, 2022 15:25 | 0 | 0
3636991 | 68240 | ATM Project | 3 | ATM_1-3 | 292268 | Bug |  |  | 63673 | 1.0 | Typo | If you try to cancel a transaction, there is a typo of the word "Wood" which should be "Would". | 3 | Resolved | 3 | Normal |  |  |  |  | 319573 | Jacob Lansang | 319573 | Jacob Lansang | Jan. 20, 2022 12:52 |  | 319573 | Jacob Lansang | Jan. 28, 2022 17:48 | 0 | 0
3637022 | 68240 | ATM Project | 5 | ATM_1-5 | 292268 | Bug | 92794 | MFT | 63673 | 1.0 | Appendix C - 23 | Cancelling a deposit transaction when the system shows a menu of account types shows incorrect spelling of "Would" for word "Wood". | 3 | Resolved | 4 | Low | [6 empty] | 319573 | Jacob Lansang | Jan. 20, 2022 13:12 |  | 319573 | Jacob Lansang | Jan. 28, 2022 17:48 | 0 | 0
3637024 | 68240 | ATM Project | 6 | ATM_1-6 | 292268 | Bug | 92794 | MFT | 63673 | 1.0 | Appendix C - 24 | Cancelling a deposit transaction when the system requests a dollar amount shows incorrect spelling of "Would" for word "Wood". | 3 | Resolved | 4 | Low | [6 empty] | 319573 | Jacob Lansang | Jan. 20, 2022 13:13 |  | 319573 | Jacob Lansang | Jan. 28, 2022 17:47 | 0 | 0
3637027 | 68240 | ATM Project | 7 | ATM_1-7 | 292268 | Bug | 92794 | MFT | 63673 | 1.0 | Appendix C - 25 | Cancelling a deposit transaction when the system asks for an envelope shows incorrect spelling of "Would" for word "Wood". | 3 | Resolved | 4 | Low | [6 empty] | 319573 | Jacob Lansang | Jan. 20, 2022 13:15 |  | 319573 | Jacob Lansang | Jan. 28, 2022 17:47 | 0 | 0
3637033 | 68240 | ATM Project | 8 | ATM_1-8 | 292268 | Bug | 92794 | MFT | 63673 | 1.0 | Appendix C - 29 | System shows an incorrect balance when performing a transfer from savings to checking. Bug was found by trying to transfer money from savings to checking account. Expected total balance is $1010.00 in both total and available balance but output terminal shows $1009.50 in both total and available balance. Log also shows incorrect amount of money transferred. Log shows a transfer of $9.50 instead of $10.00. Incorrect card number also shown on receipt. Card number should be 1 but the receipt shows 2. Defect still present in version 1.1. Wrong card number is shown on receipt. Receipt says that transfer occurred from checking to savings, instead of from savings to checking. Total balance is now correct. | 2 | In Progress | 2 | High | [6 empty] | 319573 | Jacob Lansang | Jan. 20, 2022 13:21 |  | 319573 | Jacob Lansang | Jan. 26, 2022 16:32 | 0 | 0
3637034 | 68240 | ATM Project | 9 | ATM_1-9 | 292268 | Bug | 92794 | MFT | 63673 | 1.0 | Appendix C - 30 | Cancelling a transfer transaction when the system shows a menu of account types to transfer from shows incorrect spelling of "Would" for word "Wood". | 3 | Resolved | 4 | Low | [6 empty] | 319573 | Jacob Lansang | Jan. 20, 2022 13:22 |  | 319573 | Jacob Lansang | Jan. 28, 2022 17:48 | 0 | 0
3651613 | 68240 | ATM Project | 33 | ATM_1-33 | 292268 | Bug | 92794 | MFT | 63673 | 1.0 | Appendix C - 22: Deposit error | When depositing a legitimate dollar amount, systems prints receipt incorrectly. Expected card number is 2, but the receipt shows 3. The total balance should be $125.00, but receipt shows $115.00. Defects still appear in version 1.1. When trying to deposit $10.00 into checking, receipt shows $119.90 instead of $120.00. Log shows correct amount deposited. | 2 | In Progress | 2 | High | [6 empty] | 319573 | Jacob Lansang | Jan. 26, 2022 15:02 |  | 319573 | Jacob Lansang | Jan. 26, 2022 16:31 | 0 | 0
3651712 | 68240 | ATM Project | 34 | ATM_1-34 | 292268 | Bug | 92794 | MFT | 63850 | 1.1 | MFT Appendix C - 22: Wrong total balance when depositing | When trying to make a deposit into checking account and the user is asked to insert an envelope, the receipt shows the wrong card number 2 instead of 1. The receipt also shows the wrong total balance, which should show $109.90 instead of $110.00 when trying to deposit $10.00. However, the log shows the right amount deposited. | 1 | Open | 2 | High | [6 empty] | 319573 | Jacob Lansang | Jan. 26, 2022 16:27 |  | 319573 | Jacob Lansang | Jan. 26, 2022 16:27 | 0 | 0
3645030 | 68240 | ATM Project | 14 | ATM_1-14 | 292268 | Bug |  |  | 63673 | 1.0 | Appendix C - 8 | The word "would" is spelled "wood" on the prompt screen. This was achieved via a deposit transaction interaction with a valid card and PIN. | 1 | Open | 3 | Normal | [6 empty] | 319962 | Kaitlin Culligan | Jan. 24, 2022 17:36 |  | 319962 | Kaitlin Culligan | Jan. 24, 2022 18:00 | 0 | 0
3645040 | 68240 | ATM Project | 15 | ATM_1-15 | 292268 | Bug |  |  | 63850,63673 | 1.1,1.0 | Appendix C - 12 | The select account to withdraw from screen displays a money market account for card 1 even though card 1 does not have a money market account attached to it. | 1 | Open | 3 | Normal | [6 empty] | 319962 | Kaitlin Culligan | Jan. 24, 2022 17:45 |  | 319961 | Kunal Dhawan | Jan. 24, 2022 18:01 | 0 | 0
3645043 | 68240 | ATM Project | 16 | ATM_1-16 | 292268 | Bug |  |  | 63850,63673 | 1.1,1.0 | Appendix C - 11 | When going to use the incorrect pin exception, entering the correct pin for the card will take you to the standard enter pin screen. You have to then enter the correct pin a second time in order to access the app | 1 | Open | 3 | Normal | [6 empty] | 319962 | Kaitlin Culligan | Jan. 24, 2022 17:49 |  | 319961 | Kunal Dhawan | Jan. 24, 2022 18:03 | 0 | 0
3645055 | 68240 | ATM Project | 18 | ATM_1-18 | 292268 | Bug |  |  | 63673 | 1.0 | Appendix C - 14 | When going to select a $20 withdrawal from the checking account of card 1 when there is more than $20 present in the machine, the atm withdraws $40 instead of $20. All functionality behaves as if $40 should have been withdrawn. In fact for every such transaction the amount coming out is $20 extra. | 3 | Resolved | 3 | Normal | [6 empty] | 319962 | Kaitlin Culligan | Jan. 24, 2022 17:53 |  | 319961 | Kunal Dhawan | Jan. 27, 2022 20:50 | 0 | 0
3645062 | 68240 | ATM Project | 19 | ATM_1-19 | 292268 | Bug |  |  | 63673 | 1.0 | Appendix C - 15 | When going to withdraw $200 from the checking account of card 1 when the ATM only has $20 in it, causes a withdrawal of $20. There is no prompt to select another amount. | 3 | Resolved | 3 | Normal | [6 empty] | 319962 | Kaitlin Culligan | Jan. 24, 2022 17:57 |  | 319961 | Kunal Dhawan | Jan. 24, 2022 18:15 | 0 | 0
3645093 | 68240 | ATM Project | 21 | ATM_1-21 | 292268 | Bug |  |  | 63673 | 1.0 | Appendix C - 16 | When withdrawing $200 from from the checking account of card 1 with a balance of $100 when there is $2000 in the ATM, the ATM withdraws $20 from the checking account. | 3 | Resolved | 3 | Normal | [6 empty] | 319962 | Kaitlin Culligan | Jan. 24, 2022 18:05 |  | 319961 | Kunal Dhawan | Jan. 24, 2022 18:17 | 0 | 0
3645107 | 68240 | ATM Project | 22 | ATM_1-22 | 292268 | Bug |  |  | 63673 | 1.0 | Appendix C - 17 | When canceling a withdrawal transaction from the account selection screen, the word "would" in "Would you like to do another transaction?" is spelled "Wood" | 1 | Open | 3 | Normal | [6 empty] | 319962 | Kaitlin Culligan | Jan. 24, 2022 18:07 |  | 319962 | Kaitlin Culligan | Jan. 24, 2022 18:07 | 0 | 0
3645112 | 68240 | ATM Project | 23 | ATM_1-23 | 292268 | Bug |  |  | 63673 | 1.0 | Appendix C - 18 | When canceling a withdrawal transaction from the amount selection screen, the word "would" in "Would you like to do another transaction?" is spelled "Wood" | 1 | Open | 3 | Normal | [6 empty] | 319962 | Kaitlin Culligan | Jan. 24, 2022 18:08 |  | 319962 | Kaitlin Culligan | Jan. 24, 2022 18:08 | 0 | 0
3645122 | 68240 | ATM Project | 24 | ATM_1-24 | 292268 | Bug |  |  | 63673 | 1.0 | Appendix C - 19 | The account selection screen for the deposit transaction, when used with card 1, incorrectly displays a Money Market account as an option. | 1 | Open | 3 | Normal | [6 empty] | 319962 | Kaitlin Culligan | Jan. 24, 2022 18:10 |  | 319962 | Kaitlin Culligan | Jan. 24, 2022 18:10 | 0 | 0
3644992 | 68240 | ATM Project | 10 | ATM_1-10 | 292268 | Bug |  |  |  |  | Balance inquiry | Balance Inquiry doesnt display the savings account when user inserts card 1 and shows money market even though the account doesnt have one, then enter correct card number and PIN and select Balance Inquiry. | 1 | Open | 3 | Normal | [6 empty] | 319961 | Kunal Dhawan | Jan. 24, 2022 16:58 |  | 319961 | Kunal Dhawan | Jan. 24, 2022 17:42 | 0 | 0
3645003 | 68240 | ATM Project | 11 | ATM_1-11 | 292268 | Bug |  |  |  |  | Reciept displays wrong card number | When Inserted card 1, the receipt shows the wrong card number. Enter correct card number and PIN to withdraw money or deposit money to recreate the issue. | 1 | Open | 3 | Normal | [6 empty] | 319961 | Kunal Dhawan | Jan. 24, 2022 17:02 |  | 319961 | Kunal Dhawan | Jan. 24, 2022 17:04 | 0 | 0
3645009 | 68240 | ATM Project | 12 | ATM_1-12 | 292268 | Bug |  |  |  |  | Selecting a number missing in a list hangs it, gives out $20 bills | After inserting a card, then enter correct card number and PIN, if user selects a number that isnt a listed option on any menu it hangs and keeps trying to giving $20 dollar bills out regardless of whether they are present in the machine or not. | 1 | Open | 2 | High | [6 empty] | 319961 | Kunal Dhawan | Jan. 24, 2022 17:13 |  | 319961 | Kunal Dhawan | Jan. 24, 2022 17:21 | 0 | 0
3645016 | 68240 | ATM Project | 13 | ATM_1-13 | 292268 | Bug |  |  |  |  | Entering incorrect pin makes user enter correct pin twice | Entering incorrect pin after inserting cards, makes you reenter the card pin twice to move ahead | 1 | Open | 3 | Normal | [6 empty] | 319961 | Kunal Dhawan | Jan. 24, 2022 17:16 |  | 319961 | Kunal Dhawan | Jan. 24, 2022 17:16 | 0 | 0
3645053 | 68240 | ATM Project | 17 | ATM_1-17 | 292268 | Bug |  |  | 63850 | 1.1 | Appendix C - 8 | The dollar sign is missing for 60 dollars on the withdraw page | 1 | Open | 4 | Low | [6 empty] | 319961 | Kunal Dhawan | Jan. 24, 2022 17:53 |  | 319961 | Kunal Dhawan | Jan. 24, 2022 17:53 | 0 | 0
3645143 | 68240 | ATM Project | 25 | ATM_1-25 | 292268 | Bug |  |  | 63850,63673 | 1.1,1.0 | Appendix C - 14 | Reciept displays wrong card number | 1 | Open | 3 | Normal | [6 empty] | 319961 | Kunal Dhawan | Jan. 24, 2022 18:13 |  | 319962 | Kaitlin Culligan | Jan. 24, 2022 18:15 | 0 | 0
3637011 | 68240 | ATM Project | 4 | ATM_1-4 | 292268 | Bug |  |  | 63673 | 1.0 | Testing Balance Inquiry | When Pressing transaction type 4) and then selecting 2) for which Account to inquire from, the output terminal shows that the request is inquiring the savings account and shows the balance for savings. | 1 | Open | 2 | High | [6 empty] | 319561 | LAB1-Group14 | Jan. 20, 2022 13:03 |  | 319561 | LAB1-Group14 | Jan. 20, 2022 13:03 | 0 | 0
3651476 | 68240 | ATM Project | 26 | ATM_1-26 | 292268 | Bug |  |  | 63673 | 1.0 | Appendix C - Test 31 | ![image][2022-01-26 (2).png] After pressing the "Cancel" key before selecting an account type for a transfer, the ATM displays the message "Last transaction was cancelled. Wood you like to do another transaction". There is a typo in the word Wood, as it should instead be "Would". | 3 | Resolved | 4 | Low | [6 empty] | 319561 | LAB1-Group14 | Jan. 26, 2022 12:49 |  | 319573 | Jacob Lansang | Jan. 28, 2022 17:51 | 1 | 0
3651482 | 68240 | ATM Project | 28 | ATM_1-28 | 292268 | Bug |  |  |  |  | Appendix C - Test 32 | ![image][2022-01-26 (2).png] After pressing the "Cancel" key before entering money for a transfer, the ATM displays the message "Last transaction was cancelled. Wood you like to do another transaction". There is a typo in the word Wood, as it should instead be "Would". | 1 | Open | 4 | Low | [6 empty] | 319561 | LAB1-Group14 | Jan. 26, 2022 12:55 |  | 319573 | Jacob Lansang | Jan. 28, 2022 17:51 | 1 | 0
3651485 | 68240 | ATM Project | 29 | ATM_1-29 | 292268 | Bug |  |  |  |  | Appendix C - Test 33 | After selecting Balance inquiry, the ATM only displays accounts "Checking" and "Money Market". There is no option to choose "Savings" ![image][2022-01-26 (3).png] | 1 | Open | 2 | High | [6 empty] | 319561 | LAB1-Group14 | Jan. 26, 2022 13:00 |  | 319573 | Jacob Lansang | Jan. 28, 2022 17:51 | 1 | 0
3651527 | 68240 | ATM Project | 30 | ATM_1-30 | 292268 | Bug |  |  |  |  | Appendix C - Test 34 | When requesting a Balance Inquiry for Checking Account for Card 1, Receipt displays "Card 2" | 1 | Open | 2 | High | [6 empty] | 319561 | LAB1-Group14 | Jan. 26, 2022 13:48 |  | 319561 | LAB1-Group14 | Jan. 26, 2022 13:48 | 0 | 0
3651589 | 68240 | ATM Project | 31 | ATM_1-31 | 292268 | Bug |  |  |  |  | Appendix C - Test 35 | After pressing cancel when requesting an inquiry transaction, the message has a typo in it: "Wood" instead of "Would" | 1 | Open | 4 | Low | [6 empty] | 319561 | LAB1-Group14 | Jan. 26, 2022 14:38 |  | 319573 | Jacob Lansang | Jan. 28, 2022 17:51 | 0 | 0
3651602 | 68240 | ATM Project | 32 | ATM_1-32 | 292268 | Bug |  |  |  |  | Appendix C - Test 37 | When the PIN is inputted incorrectly, it displays "PIN was incorrect Please re-renter your PIN then press ENTER". However, after inputting the correct PIN for a card, the ATM's display is "Please enter your PIN Then press ENTER" and requires the user to input the correct pin a second time. | 1 | Open | 2 | High | [6 empty] | 319561 | LAB1-Group14 | Jan. 26, 2022 14:50 |  | 319561 | LAB1-Group14 | Jan. 26, 2022 14:50 | 0 | 0
3654538 | 68240 | ATM Project | 35 | ATM_1-35 | 292268 | Bug |  |  | 63673 | 1.0 | Exploratory Testing: Money Market Inquiry dispenses $500 | After inserting the card, and inputting the correct pin, the ATM prompts for which transaction. After choosing to to a balance inquiry for the money market account, the ATM screen displays "Unknown error" and dispenses $500. Not only does it malfunction in that way, the receipt displays the wrong card number, and displays that the inquiry was from the savings account. | 1 | Open | 2 | High | [6 empty] | 319561 | LAB1-Group14 | Jan. 27, 2022 10:00 |  | 319573 | Jacob Lansang | Jan. 28, 2022 17:52 | 0 | 0